## Compliance Register
Phase 1 CLOSED ¦ Phase 2 Steps 2.1-2.6 CLOSED ¦ REQ-002, REQ-009, REQ-011, REQ-012, REQ-014, REQ-016, REQ-028, REQ-029, REQ-036, and REQ-038/040 PASS or CLOSED ¦ 40 of 40 requirements satisfied ¦ 0 unresolved
Phase 1 CLOSED ¦ Phase 2 Steps 2.1–2.6 CLOSED ¦ REQ-002, REQ-009, REQ-011, REQ-012, REQ-028, REQ-029, REQ-036, and REQ-038/040 PASS or CLOSED ¦ 38 of 40 requirements satisfied ¦ 2 unresolved: REQ-014, REQ-016
Requirement ID | PDF Page | Source Section | Source Requirement | Literal Interpretation | Owner | Baseline Status | Evidence Target / Minimum Acceptance | Step 0.2 Notes
REQ-001 | 2 | Project objective - Book medical appointments | Book medical appointments: Automate slot discovery and scheduling based on patient intent and doctor availability | The system shall automate medical appointment slot discovery and scheduling based on patient intent and doctor availability. | Project Lead | PASS | A scenario shows patient intent being interpreted, available doctor slots being discovered, and a booking being completed against availability. | Implementation: request_interpreter.py:12; healthcare_graph.py:72-109; appointment_tools.py:5-25; pipeline_runs.jsonl Gap: No functional gap found for the demonstrated PoC booking path; IDs and first-slot selection are fixed demo behavior.
REQ-002 | 2 | Project objective - Manage medical records | Manage medical records: Enable attendants to add or update structured/unstructured patient history | The system shall enable attendants to add or update both structured and unstructured patient history. | Project Lead | PASS | Evidence shows an attendant can add and update structured fields and unstructured history text, with the saved record retrievable. | CLOSED: Structured and unstructured add/update operations are exposed through the role-labeled Streamlit attendant interface and saved through the durable medical-record store. Step 2.4 UI evidence and 8/8 dispatcher tests passed; Step 2.5 restart evidence and 9/9 persistence tests passed; final full regression passed 55/55.
REQ-003 | 2 | Project objective - Retrieve medical histories | Retrieve medical histories: Summarize past diagnoses, treatments, and relevant alerts using LLMs | The system shall use an LLM to summarize past diagnoses, treatments, and relevant alerts. | Project Lead | PARTIAL | A patient history containing diagnoses, treatments, and alerts produces a traceable summary covering all three categories. | Implementation: response_synthesizer.py:12-80 summarizes MedicalRecord; schema contains diagnoses, medications, treatment_notes. Gap: No explicit relevant-alert field/path; summary is not tested specifically for all required categories.
REQ-004 | 2 | Project objective - Medical information searches | Perform medical information searches: Fetch up-to-date disease information using trusted external sources such as Medline and WHO | The system shall fetch up-to-date disease information from trusted external sources such as Medline and WHO. | Project Lead | OPEN | A live or controlled retrieval demonstrates dated disease information from an explicitly trusted external source, with source attribution. | Implementation: knowledge_base.py:1-44 contains synthetic local references with null URLs. Gap: No up-to-date retrieval from a trusted external source such as Medline or WHO.
REQ-005 | 3 | 1. Agent Planning and Goal Decomposition | Use a planner to interpret multi-step patient queries | The system shall use a planner to interpret multi-step patient queries. | Project Lead | PASS | A multi-step request produces a visible planner interpretation before execution. | CLOSED: workflow_planner.py consumes structured RequestIntent and emits an explicit pre-execution plan for the multi-step request. The Planning View displays the interpreted goal and planning basis before presenting execution outcomes. Component tests PASS; full local regression PASS; final canonical run deterministic PASS, semantic PASS, memory YES; visible evidence captured 2026-09-03.
REQ-006 | 3 | 1. Agent Planning and Goal Decomposition | Break down complex requests into sequential sub-goals | The planner shall break complex requests into sequential sub-goals. | Project Lead | PASS | The planning trace lists ordered sub-goals corresponding to each requested outcome. | CLOSED: Planner emits five ordered sub-goals mapped to the actual LangGraph sequence: patient context, medical history, FAISS medical retrieval, specialist lookup, and appointment booking. Every step displayed COMPLETED with corresponding WorkflowState evidence.
REQ-007 | 3 | 1. Agent Planning and Goal Decomposition | Identify appropriate tools or APIs to fulfill each task | The planner shall identify the appropriate tools or APIs for each task. | Project Lead | PASS | Each sub-goal is mapped to an appropriate tool or API in the planning/execution trace. | CLOSED: Every planned sub-goal identifies the exact operational tool and capability: get_patient_by_id, get_medical_record_by_patient, search_knowledge, find_doctors_by_specialty, and book_appointment. Visible Planning View and tests prove the mapping.
REQ-008 | 3 | 2. Tool and Memory Setup - APIs | Appointment booking (Doctor Schedule API) | The system shall integrate an appointment-booking capability represented by a Doctor Schedule API. | Project Lead | PARTIAL | A component-level interface can query schedule data and complete a booking through the schedule tool/API abstraction. | Implementation: doctor_tools.py:5-14 and appointment_tools.py:5-25 provide deterministic schedule/booking functions. Gap: No Doctor Schedule API/interface boundary; local mock list and function only.
REQ-009 | 3 | 2. Tool and Memory Setup - APIs | Medical history management (EHR DB or Patient DB) | The system shall integrate medical-history management through an EHR database or Patient database. | Project Lead | PASS | A component-level interface persists and retrieves patient history through the EHR/Patient DB abstraction. | CLOSED: A versioned JSON Patient DB abstraction now initializes, atomically saves, validates, and reloads MedicalRecord data. Successful attendant mutations persist immediately; write failures roll back in-memory state. Evidence: 9/9 focused tests, versioned store inspection, full Streamlit stop/restart with exact note retrieval, and final 55/55 regression. Runtime file data/medical_records.json is excluded from source control.
REQ-010 | 3 | 2. Tool and Memory Setup - APIs | Disease search (Web Search APIs, e.g., Bing Search, Medline) | The system shall integrate disease search through a Web Search API such as Bing Search or Medline. | Project Lead | OPEN | A disease query invokes a search integration and returns attributable external-source results. | Implementation: faiss_index.py searches only KNOWLEDGE_DOCUMENTS; knowledge_base.py sources are synthetic. Gap: No Web Search/Medline-style disease-search API.
REQ-011 | 3 | 2. Tool and Memory Setup - Vector DB | Use a vector database (e.g., FAISS) to store and retrieve patient summaries | The system shall use a vector database such as FAISS to store patient summaries. | Project Lead | PASS | A patient summary is embedded and stored in the vector index with a patient-linked identifier. | CLOSED: patient_summary_index.py constructs patient summaries from durable Patient and MedicalRecord state, embeds them through the unchanged embedding interface, and stores them in a FAISS IndexFlatL2 index with patient_id and record_id metadata. Evidence: 4/4 focused tests, approved live integration, and 59/59 final regression.
REQ-012 | 3 | 2. Tool and Memory Setup - Vector DB | Use a vector database (e.g., FAISS) to store and retrieve patient summaries | The vector database shall retrieve patient summaries. | Project Lead | PASS | A patient/context query retrieves the correct stored patient summary from the vector index. | CLOSED: patient-summary retrieval applies patient_id filtering before vector search, preventing cross-patient leakage. The canonical LangGraph workflow retrieved exactly one P001/R001 summary, included the durable Step 2.5 history note, and returned zero workflow errors.
REQ-013 | 3 | 2. Tool and Memory Setup - Memory | Configure memory modules to retain long-term patient context | The system shall configure memory modules that retain long-term patient context. | Project Lead | PARTIAL | Patient context remains available beyond a single immediate turn/session boundary defined by the implementation and is consumed in a later task. | Implementation: patient_memory.py:22-91 stores five turns in process; cross-turn test exists; README.md:232 declares non-persistence. Gap: Context does not survive application restart, so it is not long-term.
REQ-014 | 3 | 3. Prompt Engineering and Task Chaining | Create structured prompts tailored to each agentic sub-task | The system shall create structured prompts tailored to each agentic sub-task. | Project Lead | PARTIAL | Prompt artifacts or traces show task-specific structured prompts for the implemented sub-tasks. | Implementation: Structured prompts exist in request_interpreter.py, response_synthesizer.py, and semantic evaluator. Gap: No task-specific structured prompt for every agentic sub-task; deterministic nodes have no prompt artifacts.
REQ-015 | 3 | 3. Prompt Engineering and Task Chaining | Design prompt chains that guide LLMs through summarization, planning, and action triggering | Prompt chains shall guide the LLM through medical-history summarization. | Project Lead | PARTIAL | A trace shows ordered prompt-chain execution resulting in a history summary. | Implementation: Interpreter -> graph -> response synthesizer forms a multi-stage pipeline; synthesizer performs summary generation. Gap: No explicit prompt-chain artifact demonstrates summarization chain stages.
REQ-016 | 3 | 3. Prompt Engineering and Task Chaining | Design prompt chains that guide LLMs through summarization, planning, and action triggering | Prompt chains shall guide the LLM through planning. | Project Lead | CLOSED | Prompt-generated plan_steps verified in RequestIntent; summary-only live test passed; full regression 125 passed. | Implementation: request_interpreter now returns an ordered planning sequence. The plan is descriptive only and does not authorize tool execution.
REQ-017 | 3 | 3. Prompt Engineering and Task Chaining | Design prompt chains that guide LLMs through summarization, planning, and action triggering | Prompt chains shall guide the LLM through action triggering. | Project Lead | OPEN | A trace connects a prompt-chain decision to an authorized tool/action invocation. | Implementation: LangGraph triggers a fixed sequence; LLM outputs do not select or trigger actions. Gap: No prompt-chain-to-action trigger mechanism.
REQ-018 | 3 | 3. Prompt Engineering and Task Chaining | Incorporate patient context in prompts using memory lookups | Prompts shall incorporate patient context obtained through memory lookups. | Project Lead | OPEN | A prompt trace shows retrieved memory context incorporated into the relevant prompt without exposing inappropriate data. | Implementation: Memory is written after evaluation; narrow follow-ups read memory deterministically in assistant_pipeline.py:143-219. Gap: Memory lookup is not incorporated into any LLM prompt.
REQ-019 | 3 | 4. Agent Execution Flow - Sample scenario | Identify patient and context | For the sample multi-task scenario, the agent shall identify the patient and relevant context. | Project Lead | PASS | The scenario trace resolves the referenced patient/family context before downstream tasks. | Implementation: request_interpreter.py maps the father/CKD scenario to P001; logs show Robert Smith context. Gap: Demo mapping is hard-coded to the official scenario, limiting generality but satisfying the required sample.
REQ-020 | 3 | 4. Agent Execution Flow - Sample scenario | Retrieve father's medical history | For the sample scenario, the agent shall retrieve the father's medical history. | Project Lead | PASS | The scenario trace retrieves the correct history record for the referenced father/patient. | Implementation: healthcare_graph.py:25-39 and medical_record_tools.py:5-13 retrieve P001 history; logs contain R001. Gap: No gap for sample retrieval; record source remains mock/in-memory.
REQ-021 | 4 | 4. Agent Execution Flow - Sample scenario | Query doctor calendar and book appointment | For the sample scenario, the agent shall query the doctor calendar and book an appointment. | Project Lead | PASS | The scenario trace shows calendar query, available-slot selection, and successful booking. | Implementation: healthcare_graph.py:72-109 queries specialty matches and books first available slot; logs show A001 scheduled. Gap: No functional gap for canonical sample; API boundary handled under REQ-008.
REQ-022 | 4 | 4. Agent Execution Flow - Sample scenario | Search and summarize treatment options via RAG pipeline | For the sample scenario, the agent shall search for and summarize treatment options through a RAG pipeline. | Project Lead | PARTIAL | The scenario produces a source-grounded RAG summary of treatment options with retrieval evidence. | Implementation: healthcare_graph.py:41-69 retrieves FAISS content; response_synthesizer.py summarizes it. Gap: Retrieval is synthetic/local and covers general monitoring, not up-to-date treatment options from trusted external sources.
REQ-023 | 4 | 6. Model Evaluation | Use QAEvalChain or equivalent to assess accuracy and relevance of generated summaries and search results | The system shall use QAEvalChain or an equivalent evaluation mechanism. | Project Lead | PASS + LIMITATION | An evaluation component is identified, justified as QAEvalChain-equivalent if applicable, and executed on generated output. | Implementation: pipeline_evaluator.py and semantic_faithfulness_evaluator.py provide deterministic and LLM evaluation; README documents dual gates. Gap: Equivalent is not QAEvalChain and is scenario-tuned; equivalence rationale must be explicit in submission evidence.
REQ-024 | 4 | 6. Model Evaluation | Use QAEvalChain or equivalent to assess accuracy and relevance of generated summaries and search results | The evaluation mechanism shall assess accuracy of generated summaries and search results. | Project Lead | PASS + LIMITATION | Recorded evaluation output contains an accuracy judgment or score for both applicable output types. | Implementation: pipeline_evaluator checks structured facts; semantic evaluator judges grounded claims; six-case battery targets factual failures. Gap: No named standalone 'accuracy' metric and current live rerun is dependency-blocked in this audit environment.
REQ-025 | 4 | 6. Model Evaluation | Use QAEvalChain or equivalent to assess accuracy and relevance of generated summaries and search results | The evaluation mechanism shall assess relevance of generated summaries and search results. | Project Lead | PASS + LIMITATION | Recorded evaluation output contains a relevance judgment or score for both applicable output types. | Implementation: semantic evaluator includes retrieval_relevance_supported and notes; T06 tests irrelevant retrieval. Gap: Relevance is a boolean judgment, not an aggregate score; trusted external retrieval not yet in scope.
REQ-026 | 4 | 6. Model Evaluation | Use QAEvalChain or equivalent to assess accuracy and relevance of generated summaries and search results | Generated summaries and medical-search results shall both be included in the evaluation scope. | Project Lead | PASS + LIMITATION | Evaluation test data and results explicitly include at least one generated summary and one search result. | Implementation: Evaluators receive response_text and retrieved documents; semantic battery covers summary claims and retrieved claims. Gap: Search-result evaluation currently applies to synthetic FAISS results, not trusted external results.
REQ-027 | 4 | 6. Model Evaluation | Log and analyze agent performance per module (e.g., success rate of bookings, response precision) | The system shall log and analyze agent performance per module. | Project Lead | PARTIAL | Logs and an analysis view/report distinguish performance by agent/tool module. | Implementation: assistant_pipeline.py logs one detailed run record; JSONL contains intent, state, response, evaluations, and memory. Gap: No per-module event records or analysis by module.
REQ-028 | 4 | 6. Model Evaluation | Log and analyze agent performance per module (e.g., success rate of bookings, response precision) | Per-module performance analysis shall include appointment-booking success rate. | Project Lead | PASS | A reproducible booking-success metric is calculated from persisted TOOL_EXECUTION booking outcomes and displayed in Streamlit. | CLOSED: Operational Performance panel aggregates persisted book_appointment TOOL_EXECUTION events: 9 successful bookings / 11 attempts = 81.82%, with 2 failed bookings. Records scanned 52; malformed records skipped 0; skipped booking steps excluded from denominator. Focused tests 10 passed; full regression 121 passed; persisted metric proof passed; memory file unchanged. Visible evidence: REQ_028_Operational_Performance_Evidence.png.
REQ-029 | 4 | 6. Model Evaluation | Log and analyze agent performance per module (e.g., success rate of bookings, response precision) | Per-module performance analysis shall include response precision. | Project Lead | PASS | A defined and reproducible response-precision measure is calculated from persisted semantic-evaluation records and displayed in Streamlit. | CLOSED: Claim-level response precision counts structured and retrieved response claims from persisted semantic-evaluation records; authority, safety, and relevance flags are excluded. Integration result: 85 supported claims / 86 verifiable claims = 98.84%. Focused tests 14 passed; full regression 125 passed; visible evidence: REQ_029_Response_Precision_Evidence.png.
REQ-030 | 4 | 7. Data Visualization and UI | Build a Streamlit dashboard that enables: | The system shall provide a Streamlit dashboard. | Project Lead | PASS | The application launches in Streamlit and exposes the required dashboard functions. | Implementation: app/ui/streamlit_app.py configures and renders the interactive dashboard. Gap: Runtime UI launch was not repeated in this audit because project dependencies are unavailable locally; source and prior evidence exist.
REQ-031 | 4 | 7. Data Visualization and UI | Patient and doctor views | The Streamlit dashboard shall provide a patient view. | Project Lead | PASS | Visible evidence shows a distinct patient-facing view and its functional controls/output. | Implementation: streamlit_app.py:42-101 accepts patient workflow request and displays assistant response; appointment, sources, and memory follow. Gap: Patient ID is fixed to P001, appropriate only to the demo scope.
REQ-032 | 4 | 7. Data Visualization and UI | Patient and doctor views | The Streamlit dashboard shall provide a doctor view. | Project Lead | PASS | Visible evidence shows a distinct doctor-facing view and its functional controls/output. | CLOSED: Distinct Doctor View displays doctor Sarah Chen, specialty Nephrology, assigned patient Robert Smith, patient ID P001, appointment time 2026-09-02 09:00, reason, and scheduled status from authoritative WorkflowState. Component tests PASS (2/2); focused evaluator regression PASS (4/4 total); final canonical run: deterministic PASS, semantic PASS, accepted for memory YES. Visible evidence: Doctor View and Evaluation Status screenshots captured 2026-09-03.
REQ-033 | 4 | 7. Data Visualization and UI | Real-time appointment tracking | The Streamlit dashboard shall provide real-time appointment tracking. | Project Lead | PARTIAL | A booking/status change is reflected in the dashboard during the running workflow without a static-only mockup. | Implementation: Streamlit displays the latest appointment time/status from last_run. Gap: No appointment tracker/history or observable status updates beyond one static result.
REQ-034 | 4 | 7. Data Visualization and UI | Summary of latest retrieved medical information | The Streamlit dashboard shall display a summary of the latest retrieved medical information. | Project Lead | PASS | The dashboard visibly presents the most recently retrieved medical-information summary and its source context. | Implementation: streamlit_app.py:200-247 displays retrieved source title, type, URL when present, content, and distance for last_run. Gap: Current sources are synthetic and lack URLs; trusted-source closure is separate.
REQ-035 | 4 | 7. Data Visualization and UI | Evaluation metrics for model responses and tool success | The Streamlit dashboard shall display evaluation metrics for model responses. | Project Lead | PASS | Visible dashboard evidence displays model-response evaluation metrics generated by the evaluation mechanism. | CLOSED: Evaluation Status now explicitly labels Model Response Metrics and displays deterministic PASS, semantic PASS, and accepted-for-memory YES from the existing evaluation payload. Component metrics tests PASS (3/3); focused and full suites PASS (10/10); visible canonical evidence captured 2026-09-03.
REQ-036 | 4 | 7. Data Visualization and UI | Evaluation metrics for model responses and tool success | The Streamlit dashboard shall display evaluation metrics for tool success. | Project Lead | PASS | Visible dashboard evidence displays tool success metrics derived from logged tool outcomes. | CLOSED: Tool Success Metrics visibly aggregate the executed planning outcomes into Tools Attempted 5, Tools Successful 5, Tools Failed 0, and Tool Success Rate 100%. Success, partial-failure, and zero-attempt calculations are component tested. Canonical evidence screenshots: 5312cc2e-0773-4d7f-a877-72e49e3f0bc3.png, a7a26a90-22ce-4364-9fb8-d8f10b5f66ae.png, a6b1d66b-9a11-47c0-9051-dab4cafdaa08.png.
REQ-037 | 4 | 8. Memory and Logs Interface | Display agent memory traces and planning breakdowns | The interface shall display agent memory traces. | Project Lead | PARTIAL | A visible interface section displays memory retrieval/write traces for a test scenario. | Implementation: streamlit_app.py:251-284 displays stored memory fields/turn count; assistant_pipeline gates writes. Gap: No memory read/write trace or provenance/timestamp/action display.
REQ-038 | 4 | 8. Memory and Logs Interface | Display agent memory traces and planning breakdowns | The interface shall display planning breakdowns. | Project Lead | PASS | A visible interface section displays the ordered plan/sub-goals for a test scenario. | CLOSED: Distinct Planning View displays the goal, Structured RequestIntent planning basis, LangGraph execution framework, five ordered sub-goals, graph nodes, tools/capabilities, COMPLETED status, and populated WorkflowState evidence. Component tests 3/3 PASS; focused suite 7/7 PASS; full suite 7/7 PASS; canonical run deterministic PASS, semantic PASS, memory YES. Evidence screenshots: a258b80f-00d4-4ece-8b70-294a4f3a5f14.png, adef6ba0-2073-43b7-92f1-501e109b1ed7.png, d2010770-9502-4ca7-b05f-642dab903b0c.png.
REQ-039 | 4 | 8. Memory and Logs Interface | Include interactive elements to test different user scenarios | The interface shall include interactive elements for testing different user scenarios. | Project Lead | PARTIAL | A user can select or enter multiple scenarios and execute them through the application interface. | Implementation: Streamlit text area permits arbitrary request entry and Run Assistant execution. Gap: Only one patient is selectable and the pipeline is strongly tuned to the canonical scenario; no curated multi-scenario controls/evidence.
REQ-040 | 4 | 8. Memory and Logs Interface | Log tool usage and success/failure across tasks | The system shall log tool usage and success/failure across tasks. | Project Lead | PASS | Logs identify each tool invocation, task association, and success/failure outcome across representative workflows. | CLOSED: run_result now contains five ordered TOOL_EXECUTION records with tool, LangGraph node, capability, SUCCESS/FAILURE status, and execution evidence. The existing pipeline logger persists the records in logs/pipeline_runs.jsonl and Workflow Diagnostics displays the same records. Component tests PASS (3/3); full regression PASS (13/13); canonical live run PASS/PASS/YES with 5/5 tools successful; JSONL inspection confirmed five persisted SUCCESS events. Evidence captured 2026-09-03.
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The source says trusted external sources such as Medline and WHO. Architectural similarity to a local knowledge base is not sufficient unless the source permits equivalence.

## Control Notes
Phase 0 - Step 0.1 Control Notes
Controlling specification | Capstone_problem_statement_agentic_healthcare_assistant_for_medical_task_(1).pdf
Source scope | Official four-page Capstone Problem Statement
Requirement count
Acceptance chain | Source Requirement -> Literal Interpretation -> Existing Implementation -> Gap -> Smallest Compliant Implementation -> Component Test -> Integration Test -> Visible Evidence -> CLOSED
Current boundary | Source Requirement + Literal Interpretation + minimum acceptance evidence only
Implementation assessment | Not performed in Step 0.1; required in Step 0.2
Code changes | None
Canonical workflow | PRESERVED: structured request interpretation -> LangGraph orchestration -> deterministic tools -> FAISS/RAG -> response synthesis -> dual evaluation -> memory/logging -> Streamlit
Optional work | Frozen until all explicit capstone requirements are closed; Docker excluded from current critical path
Closure rule | No row may be CLOSED until behavior is implemented, component-tested, integration-tested, and supported by visible submission evidence
Phase 0 status | Steps 0.1, 0.2, and 0.3 CLOSED as governance/mapping steps
Scope freeze | Phase 0 and Phase 1 CLOSED; Phase 2 Steps 2.1–2.6 CLOSED
Current Work model | GPT-5.6 Sol Light; any change requires Francisco Soto approval
Application model state | UNCHANGED; any LLM/embedding/evaluator model change requires approval
Next authorized work | Phase 3 trusted external retrieval - REQ-004/010/022/026; approval and source-contract gate required
Code modification in Step 1.1 | Added Doctor View projection/tab/tests and bounded appointment-time evaluator format correction; canonical backend and models unchanged
Step 1.1 status | CLOSED - component, canonical integration, dual evaluation, memory acceptance, and visible Doctor View evidence passed
Step 2.4 status | CLOSED - attendant UI component tests, four visible mutation behaviors, safeguards, and 46/46 regression tests passed
REQ-002 status | PASS - attendants can add/update structured and unstructured history through the Streamlit interface
Prior limitation | CLOSED - patient-history changes now survive complete Streamlit shutdown and restart
Step 2.5 status | CLOSED - 9/9 persistence tests, 55/55 final regression, disk inspection, and visible restart retrieval passed
REQ-009 status | PASS - versioned Patient DB abstraction persists and retrieves structured/unstructured MedicalRecord state
Persistence boundary | Local JSON PoC storage with atomic replacement and rollback; production EHR integration remains outside the capstone PoC
Step 2.6 status | CLOSED - 4/4 focused tests, approved live integration, and 59/59 final regression passed
REQ-011 status | PASS - FAISS stores patient summaries with patient_id and record_id metadata
REQ-012 status | PASS - patient-scoped retrieval returns the correct summary and prevents cross-patient leakage
Embedding boundary | Existing text-embedding-3-small identifier unchanged; deterministic embeddings used for component tests; one approved live workflow used for integration evidence
REQ-028 status | CLOSED - additive persisted booking-success metric: 9/11 = 81.82%; 52 records scanned; 0 malformed; focused 10/10 and full 121/121 passed; visible Operational Performance evidence captured; no paid model calls required for metric proof.
REQ-029 status | CLOSED - claim-level response precision defined as supported verifiable claims divided by total verifiable claims; persisted integration produced 85/86 = 98.84%; focused 14/14 and full 125/125 passed; visible evidence captured; no paid model calls required.

## Delta Log
Delta - Phase 0, Steps 0.1-0.3
Classification | Item | What Changed | Why | Verification
PRESERVED | Validated canonical workflow | No architecture or code change. | Step 0.1 is a requirements-control action only. | No code files were opened or modified.
ADDED | Definitive 40-row source register | Every explicit directive is assigned source wording, a traceable ID, literal interpretation, owner, baseline status, and evidence target. | Satisfies Step 0.1 exit control and prevents adjacent capabilities from being accepted as literal compliance. | Register count reconciles to 40 populated requirement IDs.
REMOVED | None | No application capability, artifact, or prior evidence was removed. | Removal is outside Step 0.1 scope. | Delta review.
WHY | Baseline status reset to UNASSESSED - STEP 0.2 | No existing PASS/PARTIAL/OPEN judgment is copied into the source baseline. | Implementation and evidence mapping must be performed against the existing repository in Step 0.2. | All 40 baseline status cells use the same controlled value.
PRESERVED | Canonical architecture | No application code or business logic changed. | Step 0.2 is assessment and traceability only. | ZIP source tree remains unchanged.
ADDED | Step 0.2 Mapping and Summary | 40 implementation/gap/test/evidence mappings plus conservative statuses. | Creates the required traceability chain before implementation. | 40/40 mappings populated.
REMOVED | None | No requirement, capability, or evidence removed. | Preservation boundary maintained. | Read-only code audit.
WHY | No functional requirement marked CLOSED | PASS describes current evidence only; closure still requires final component/integration/visible evidence reconciliation. | Matches the governing acceptance method. | Closure column remains NOT CLOSED for all 40 rows.
PRESERVED | Validated architecture and current models | No application code, workflow, LLM, embedding, or evaluator model changed. | Step 0.3 establishes governance only. | Submitted source tree unchanged.
ADDED | Scope freeze and change-control baseline | Twelve controls, locked critical-path sequence, and model/API approval template. | Prevents scope drift, silent model changes, avoidable API cost, and regression stacking. | All controls marked ACTIVE or FROZEN.
REMOVED | None | No feature, requirement, evidence, or architecture removed. | Preservation boundary maintained. | Document-only update.
WHY | Phase 0 gate established | Implementation may now begin one requirement package at a time, starting with Doctor View. | Matches the controlling project plan dependency order. | Phase 0 exit decision recorded.
PRESERVED | Canonical workflow and Patient View | No graph, tool, retrieval, evaluation, memory, model, or API configuration changed. | Doctor View reads the existing workflow output contract. | AST regression PASS across 30 Python files.
ADDED | Phase 1 Step 1.1 Doctor View implementation | Pure workflow-state projection, distinct Doctor View tab, required clinician fields, and two focused tests. | Closes the implementation gap without backend duplication. | Doctor View contract tests PASS (2/2).
REMOVED | None | No feature, requirement, evidence, or architecture removed. | Preservation boundary maintained. | Source review.
WHY | REQ-032 literal compliance | The official specification requires patient and doctor views; the project plan requires doctor, specialty, assigned patient, appointment time, reason, and status. | A distinct role-aligned view is required; an adjacent appointment summary is insufficient. | Closure withheld pending runtime integration and visible UI evidence.
PRESERVED | Canonical architecture and API model configuration | Doctor View consumes existing WorkflowState; no graph, tool, RAG, memory, model, or prompt contract changed. | Maintains the validated architecture while closing a presentation requirement. | Final canonical run: deterministic PASS, semantic PASS, memory YES.
ADDED | REQ-032 closure evidence | Distinct Doctor View, required clinician fields, four focused tests, bounded timestamp-format recognition, and two UI evidence captures. | Completes implementation, component, integration, and visible-evidence gates. | Doctor View and evaluation screenshots captured 2026-09-03.
REMOVED | None | No application capability, requirement, or evidence removed. | Preservation boundary maintained. | Delta review.
WHY | Literal patient-and-doctor-view compliance | The source requires a doctor view; the plan requires doctor, specialty, assigned patient, appointment time, reason, and status. | Visible clinician-facing evidence now matches the controlling acceptance criteria. | REQ-032 marked CLOSED only after every acceptance link passed.
PRESERVED | Canonical architecture and model configuration | Planner consumes existing RequestIntent; LangGraph order, tools, RAG, synthesis, evaluation, memory, Doctor View, and model choices remain unchanged. | Closes visibility without destabilizing execution. | Focused and full local suites 7/7; canonical PASS/PASS/YES.
ADDED | Phase 1 Step 1.2 planning/decomposition visibility | Deterministic workflow planner, five ordered sub-goals, node/tool/capability mappings, execution outcomes, Planning View, and three tests. | Closes REQ-005, REQ-006, REQ-007, and REQ-038. | Three planning screenshots plus automated test evidence.
REMOVED | None | No application capability, requirement, evidence, model, or prompt removed. | Preservation boundary maintained. | Delta review.
WHY | Literal planning and goal-decomposition compliance | The controlling specification requires planner interpretation, sequential sub-goals, tool/API identification, and a displayed planning breakdown. | Previously implicit graph structure is now explicit and tied to actual execution evidence. | Requirements marked CLOSED only after the full acceptance chain passed.
PRESERVED | Canonical architecture, evaluation engines, and Step 1.1/1.2 views | Metrics consume existing detailed result and planning outcomes; no graph, tool, RAG, model, prompt, evaluator, memory, or logging contract changed. | Maintains validated behavior and Step 1.4 boundary. | Focused and full suites 10/10; canonical PASS/PASS/YES.
ADDED | Phase 1 Step 1.3 rubric-readable metrics | Model Response Metrics plus Tools Attempted, Successful, Failed, and Success Rate; three deterministic metric tests. | Closes REQ-035 and REQ-036. | Visible values: PASS/PASS/YES and 5/5/0/100%.
REMOVED | None | No capability, requirement, evidence, model, prompt, or event-log behavior removed. | Preservation boundary maintained. | Delta review.
WHY | Literal model/tool metric compliance | The source requires dashboard metrics for model responses and tool success; Planning View outcomes alone were adjacent evidence, not an aggregate metric display. | Presentation-only aggregation is the smallest compliant implementation. | Requirements closed only after automated and visible evidence passed.
PRESERVED | Canonical architecture and model configuration | Existing LangGraph sequence, tools, RAG, prompts, evaluators, memory gate, views, and model choices remain unchanged. | Adds observability without changing workflow execution. | Component 3/3; full suite 13/13; canonical PASS/PASS/YES.
ADDED | Phase 1 Step 1.4 per-tool event contract | Pure tool-event projection, tool_events run-result field, JSONL persistence test, and Workflow Diagnostics table. | Closes REQ-040 with reviewer-inspectable tool/task/outcome evidence. | Five UI events and five persisted JSONL SUCCESS events.
REMOVED | None | No capability, requirement, evidence, model, prompt, graph node, or tool removed. | Preservation boundary maintained. | Delta review.
WHY | Literal logging and diagnostics compliance | The source requires tool usage and success/failure to be logged across tasks; aggregate Step 1.3 metrics alone did not identify individual tool outcomes. | Explicit ordered events are the smallest compliant logging contract. | REQ-040 closed only after component, integration, UI, and persisted-log evidence passed.
Phase 1 / Step 1.5 | PRESERVED | Canonical architecture and all Step 1.1–1.4 behavior | No application code added in Step 1.5; verification only | Fresh patient/doctor regression retained the canonical workflow, evaluation, memory, and diagnostics behavior
Phase 1 / Step 1.5 | ADDED | Phase 1 exit-gate evidence | Fresh Patient View and Doctor View screenshots plus final 13/13 test-suite result | Makes the post-Step 1.4 UI regression independently auditable
Phase 1 / Step 1.5 | REMOVED | None | No feature, interface, or evidence removed | Smallest compliant action was regression verification
Phase 1 / Step 1.5 | WHY | Close the Phase 1 UI regression gate | Both views operated without breaking the canonical scenario; full suite passed | Satisfies the controlling plan before Phase 2 begins
Phase 2 / Step 2.2 | PRESERVED | Validated canonical workflow, graph, UI, prompts, model configuration, retrieval, evaluation, logging, and memory | Only the medical-record tool boundary and its component tests changed | 26/26 full regression tests passed
Phase 2 / Step 2.2 | ADDED | Deterministic structured-history mutation interface | Add/update diagnoses, medications, and treatment notes with explicit result statuses | 13/13 component tests passed
Phase 2 / Step 2.2 | REMOVED | None | No interface, feature, evidence, or requirement removed | Preservation boundary maintained
Phase 2 / Step 2.2 | WHY | Close the structured portion of medical-history management | Authoritative in-memory MedicalRecord objects now reflect validated add/update operations | REQ-002 remains OPEN until unstructured history and attendant UI pass
Phase 2 / Step 2.3 | PRESERVED | Step 2.2 structured mutations and validated canonical architecture | Graph, UI, persistence, prompts, model configuration, and API behavior unchanged | 38/38 regression tests passed
Phase 2 / Step 2.3 | ADDED | Unstructured patient-history note path | MedicalRecord.history_notes plus deterministic add/update operations and component tests | 12/12 component tests passed
Phase 2 / Step 2.3 | REMOVED | None | No interface, feature, evidence, or requirement removed | Preservation boundary maintained
Phase 2 / Step 2.3 | WHY | Close the unstructured data-path portion of medical-history management | Free text and internal line breaks are preserved; failures return explicit statuses | REQ-002 remains OPEN until Step 2.4 attendant UI passes
Phase 2 / Step 2.4 | PRESERVED | Validated canonical workflow, Step 2.2 structured mutations, and Step 2.3 unstructured note tools | Graph, prompts, model configuration, retrieval, evaluation, logging, and memory contracts unchanged | 46/46 full regression tests passed
Phase 2 / Step 2.4 | ADDED | Smallest compliant attendant/history-management UI | Role-labeled Streamlit controls dispatch structured and unstructured add/update actions and display retrievable current history | 8/8 dispatcher component tests and four visible UI behaviors passed
Phase 2 / Step 2.4 | REMOVED | None | No feature, interface, evidence, or requirement removed | Preservation boundary maintained
Phase 2 / Step 2.4 | WHY | Close REQ-002 at the attendant interaction boundary | The UI now provides safe add/update controls, explicit success/failure feedback, and visible current-history evidence | REQ-002 PASS; restart persistence remains separately tracked under REQ-009 / Step 2.5
Phase 2 / Step 2.5 | PRESERVED | Validated workflow, history schemas, deterministic mutation tools, attendant UI, prompts, model configuration, retrieval, evaluation, logging, and memory | Persistence wraps accepted mutations without changing existing business logic | 55/55 final regression tests passed
Phase 2 / Step 2.5 | ADDED | Durable versioned patient-history store | Atomic JSON save/load/initialize boundary, startup reload, environment path override, rollback on write failure, and focused tests | 9/9 persistence component tests and independent restart evidence passed
Phase 2 / Step 2.5 | REMOVED | None | No feature, interface, evidence, patient seed, or requirement removed | Runtime JSON is excluded from source control; original source files were backed up
Phase 2 / Step 2.5 | WHY | Close durable Patient DB persistence and retrieval | Accepted history mutations now survive full application shutdown and are loaded by a new Streamlit process | REQ-009 PASS; local JSON is the bounded PoC database abstraction
Phase 2 / Step 2.6 | PRESERVED | Validated LangGraph sequence, educational FAISS retrieval, durable Patient DB, prompts, model identifiers, synthesis, evaluation, memory, logging, and UI | Added one scoped retrieval node without replacing the canonical workflow | 59/59 final regression tests passed
Phase 2 / Step 2.6 | ADDED | FAISS patient-summary storage and retrieval | PatientSummary model, durable-state summary builder, patient-linked metadata, pre-search patient filtering, graph integration, and four focused tests | Live workflow returned one P001/R001 summary containing the persisted history note
Phase 2 / Step 2.6 | REMOVED | None | No existing retrieval, model, feature, evidence, or requirement removed | Existing text-embedding-3-small configuration remained unchanged
Phase 2 / Step 2.6 | WHY | Close explicit vector database requirements | The system now stores and retrieves patient summaries through FAISS while enforcing patient identity isolation | REQ-011 and REQ-012 PASS
REQ-028 / Phase 4 | ADDED | Persisted booking-success metric and Operational Performance panel | booking_metrics.py aggregates persisted book_appointment TOOL_EXECUTION SUCCESS/FAILURE outcomes; UI displays rate, numerator, denominator, failures, formula, provenance, scan count, and malformed-row count outside the current-run guard | Focused 10/10; full regression 121/121; persisted proof 9/11 = 81.82%; visible screenshot; memory unchanged
REQ-029 / Phase 4 | ADDED | Persisted response-precision metric | Added strict result model, deterministic fixture evaluator, persisted semantic-evaluation aggregation, focused tests, and Streamlit display using actual pipeline_runs.jsonl records | Focused 14/14; full regression 125/125; persisted proof 85/86 = 98.84%; visible screenshot

## Step 0.2 Mapping
Phase 0 - Step 0.2 ¦ Implementation, Gap, Test, and Evidence Mapping
Assessment boundary: submitted ZIP, source inspection, existing logs/tests, and non-writing verification. No application code modified.
Requirement ID | Status | Existing Implementation / Evidence | Exact Gap | Smallest Compliant Implementation | Component Test | Integration Test | Visible Evidence | Assessment Basis | Closure
REQ-001 | PASS | request_interpreter.py:12; healthcare_graph.py:72-109; appointment_tools.py:5-25; pipeline_runs.jsonl | No functional gap found for the demonstrated PoC booking path; IDs and first-slot selection are fixed demo behavior. | Preserve implementation; later add direct booking component evidence to submission package. | Test available and unavailable slot, verify slot removal and scheduled Appointment. | Run canonical CKD request and confirm interpreted specialty, doctor availability, and booked appointment. | Test output plus Streamlit appointment screenshot and sanitized JSONL trace. | Direct code trace + prior successful run record. | NOT CLOSED
REQ-002 | OPEN | medical_record_tools.py:5-13 only retrieves; MedicalRecord schema has structured lists. | No attendant-facing add/update operation; no unstructured note field or mutation UI. | Add deterministic add/update service, unstructured note field/path, and smallest attendant UI interaction. | Create/update structured fields and unstructured note; retrieve saved values; reject invalid patient/record. | Mutate a record through UI/service, run workflow, and confirm updated authoritative state appears. | Before/after record evidence, test output, attendant UI screenshot. | Literal mutation requirement absent. | NOT CLOSED
REQ-003 | PARTIAL | response_synthesizer.py:12-80 summarizes MedicalRecord; schema contains diagnoses, medications, treatment_notes. | No explicit relevant-alert field/path; summary is not tested specifically for all required categories. | Add relevant alerts to schema/data and require summary coverage with a focused test. | Given diagnoses, treatments, and alerts, assert summary contains each supported fact. | Run workflow with alert-bearing record and verify grounded summary/evaluations. | Summary screenshot, test result, structured-state trace. | LLM summary exists; one required content category is absent. | NOT CLOSED
REQ-004 | OPEN | knowledge_base.py:1-44 contains synthetic local references with null URLs. | No up-to-date retrieval from a trusted external source such as Medline or WHO. | Add one trusted external medical retrieval adapter with date/provenance and graceful failure. | Query known disease; validate trusted domain, URL, title/content, retrieval date; test empty/failure response. | Run canonical scenario through adapter and confirm sourced output remains educational. | Retrieved-source UI screenshot with URL/date plus success/failure tests. | Synthetic local RAG is not equivalent to explicit external retrieval. | NOT CLOSED
REQ-005 | PASS | workflow_planner.py consumes RequestIntent and emits an explicit plan before graph invocation. | None for the canonical multi-step planning requirement. | Implemented bounded deterministic planner representation without adding an LLM call. | PASS: planner decomposition and planning-basis contract. | PASS: plan returned with detailed pipeline and matched post-run state. | Planning View screenshots and 7/7 focused test evidence. | Explicit planner now interprets structured intent into a visible execution plan. | CLOSED
REQ-006 | PASS | Five ordered sub-goals are emitted and displayed in actual LangGraph order. | None for sequential canonical decomposition. | Implemented explicit ordered sub-goals and execution outcome projection. | PASS: exact ordered node list and incomplete-step behavior. | PASS: all five canonical steps displayed COMPLETED with state evidence. | Planning screenshots cover Steps 1-5. | Planner decomposition is explicit, ordered, and tied to execution. | CLOSED
REQ-007 | PASS | Each sub-goal maps to an exact tool identifier and operational capability. | None for canonical tool/API identification. | Implemented allowed deterministic mapping to existing tools and API-style capabilities. | PASS: exact tool list asserted. | PASS: tool mappings correspond to populated execution-state fields. | Planning screenshots show every tool/capability. | Tool selection is visible and auditable while deterministic authority is preserved. | CLOSED
REQ-008 | PARTIAL | doctor_tools.py:5-14 and appointment_tools.py:5-25 provide deterministic schedule/booking functions. | No Doctor Schedule API/interface boundary; local mock list and function only. | Wrap existing logic behind a schedule repository/API-style interface without duplicating business logic. | Query schedule, book valid slot, reject unavailable slot. | Canonical graph uses interface and preserves booking regression. | Component output, integration trace, appointment screenshot. | Booking behavior exists; required API integration form is incomplete. | NOT CLOSED
REQ-009 | PARTIAL | mock_data.py provides records; medical_record_tools.py retrieves from an in-memory list. | No EHR/Patient DB persistence or mutation interface. | Introduce a small repository backed by local persistent storage appropriate for the PoC. | CRUD structured/unstructured history and persistence checks. | Workflow reads updated record after process restart. | Repository tests, restart proof, UI screenshot. | Read-only mock list is not an EHR/Patient DB integration. | NOT CLOSED
REQ-010 | OPEN | faiss_index.py searches only KNOWLEDGE_DOCUMENTS; knowledge_base.py sources are synthetic. | No Web Search/Medline-style disease-search API. | Implement trusted-source disease-search adapter and normalize to RetrievedDocument. | Success, no-result, timeout/error, and provenance validation tests. | Canonical request retrieves trusted external result through existing RAG contract. | Source URL/date screenshot and tests. | External search integration absent. | NOT CLOSED
REQ-011 | PASS | patient_summary_index.py builds FAISS patient-summary vectors with patient_id and record_id metadata from durable Patient/MedicalRecord state. | None after Step 2.6 closure. | Add patient-summary document construction and indexing with patient ID metadata. | PASS: metadata, durable-history rebuild, and embedding/index behavior. | PASS: live workflow returned P001/R001 summary with zero errors. | Focused-test, live-integration, and final-regression terminal evidence. | FAISS now stores the required patient-summary object. | CLOSED
REQ-012 | PASS | search_patient_summaries() filters candidates by patient_id before FAISS search; healthcare_graph.py retrieves the patient summary after medical-record retrieval. | None after Step 2.6 closure. | Add patient-summary search/retrieval with patient identity controls. | PASS: patient-scoped search and cross-patient isolation. | PASS: canonical workflow returned exactly one correct patient summary. | Live trace displays patient ID, record ID, distance, summary, and PASS decisions. | Patient-summary retrieval is present and identity-scoped. | CLOSED
REQ-013 | PARTIAL | patient_memory.py:22-91 stores five turns in process; cross-turn test exists; README.md:232 declares non-persistence. | Context does not survive application restart, so it is not long-term. | Persist validated patient memory in a simple local store and reload safely. | Write, restart/reinstantiate, recall, update, and clear tests. | Run canonical interaction, restart, answer follow-up from restored context. | Restart transcript, persistence test, memory UI evidence. | Cross-turn memory works only within one process. | NOT CLOSED
REQ-014 | PARTIAL | Structured prompts exist in request_interpreter.py, response_synthesizer.py, and semantic evaluator. | No task-specific structured prompt for every agentic sub-task; deterministic nodes have no prompt artifacts. | Document prompt/tool responsibility and add structured planner/sub-task prompts only where LLM reasoning is intended. | Validate expected prompt schemas/fields for each LLM sub-task. | Trace prompts to planning, summarization, and allowed actions. | Prompt inventory and selected trace excerpts. | Several structured prompts exist, but coverage is incomplete. | NOT CLOSED
REQ-015 | PARTIAL | Interpreter -> graph -> response synthesizer forms a multi-stage pipeline; synthesizer performs summary generation. | No explicit prompt-chain artifact demonstrates summarization chain stages. | Make the existing stages explicit in a traceable chain definition. | Assert summarization chain order and required inputs. | Canonical workflow emits chain trace and grounded summary. | Chain trace plus summary/evaluation evidence. | Functional sequence exists; prompt-chain evidence is incomplete. | NOT CLOSED
REQ-016 | OPEN | No planning prompt chain; RequestIntent only extracts patient_id, specialty, and reason. | Planning is not produced through a prompt chain. | Add bounded plan-generation/validation chain feeding existing orchestration. | Test plan schema, ordering, and unsupported-request handling. | Plan aligns with executed nodes/tools. | Planning-chain trace and test output. | Literal planning-chain behavior absent. | NOT CLOSED
REQ-017 | OPEN | LangGraph triggers a fixed sequence; LLM outputs do not select or trigger actions. | No prompt-chain-to-action trigger mechanism. | Use validated planner output to request only allow-listed actions, with deterministic enforcement. | Valid action mapping and blocked unsupported action tests. | Trace requested action -> validated tool -> result. | Action trace with success/failure evidence. | Fixed orchestration is not prompt-guided action triggering. | NOT CLOSED
REQ-018 | OPEN | Memory is written after evaluation; narrow follow-ups read memory deterministically in assistant_pipeline.py:143-219. | Memory lookup is not incorporated into any LLM prompt. | Add safe memory retrieval and inject bounded patient context into the relevant planning/summary prompt. | Assert correct patient memory inclusion and cross-patient exclusion. | Follow-up workflow uses retrieved memory context and remains grounded. | Prompt trace showing bounded memory context plus tests. | Memory consumption exists, but not in prompts as required. | NOT CLOSED
REQ-019 | PASS | request_interpreter.py maps the father/CKD scenario to P001; logs show Robert Smith context. | Demo mapping is hard-coded to the official scenario, limiting generality but satisfying the required sample. | Preserve for compliance; document PoC boundary. | Interpret official scenario and assert P001/context fields. | Run official scenario through full pipeline. | Intent and patient-state trace. | Direct implementation and prior run evidence. | NOT CLOSED
REQ-020 | PASS | healthcare_graph.py:25-39 and medical_record_tools.py:5-13 retrieve P001 history; logs contain R001. | No gap for sample retrieval; record source remains mock/in-memory. | Preserve; later replace repository under REQ-009 without changing consumer contract. | Known/missing patient record tests. | Official scenario returns correct medical record. | Workflow-state trace and UI screenshot. | Direct sample-scenario implementation. | NOT CLOSED
REQ-021 | PASS | healthcare_graph.py:72-109 queries specialty matches and books first available slot; logs show A001 scheduled. | No functional gap for canonical sample; API boundary handled under REQ-008. | Preserve behavior while introducing interface abstraction later. | Doctor match and booking availability tests. | Official scenario produces scheduled appointment. | Test output and appointment screenshot. | Direct scenario behavior with prior successful trace. | NOT CLOSED
REQ-022 | PARTIAL | healthcare_graph.py:41-69 retrieves FAISS content; response_synthesizer.py summarizes it. | Retrieval is synthetic/local and covers general monitoring, not up-to-date treatment options from trusted external sources. | Route trusted-source results through existing RetrievedDocument/RAG synthesis contract. | Relevant treatment-information retrieval and grounded-summary tests. | Official scenario retrieves and summarizes trusted current information. | Source-attributed RAG screenshot and evaluation output. | RAG pipeline exists; required information source/content remains incomplete. | NOT CLOSED
REQ-023 | PASS + LIMITATION | pipeline_evaluator.py and semantic_faithfulness_evaluator.py provide deterministic and LLM evaluation; README documents dual gates. | Equivalent is not QAEvalChain and is scenario-tuned; equivalence rationale must be explicit in submission evidence. | Preserve dual evaluators and document functional equivalence and limits. | Run known-good and adversarial evaluator battery. | Canonical output passes both gates before memory acceptance. | Evaluator report, battery output, UI details. | Source explicitly permits an equivalent. | NOT CLOSED
REQ-024 | PASS + LIMITATION | pipeline_evaluator checks structured facts; semantic evaluator judges grounded claims; six-case battery targets factual failures. | No named standalone 'accuracy' metric and current live rerun is dependency-blocked in this audit environment. | Define existing fact-consistency/faithfulness results as accuracy measures and retain rerunnable evidence. | Run known-good, wrong dose, invented diagnosis, and unsupported claim cases. | Evaluate canonical summary and trusted-search output after retrieval closure. | Battery results and metric definitions. | Equivalent accuracy assessment exists with documentation limitation. | NOT CLOSED
REQ-025 | PASS + LIMITATION | semantic evaluator includes retrieval_relevance_supported and notes; T06 tests irrelevant retrieval. | Relevance is a boolean judgment, not an aggregate score; trusted external retrieval not yet in scope. | Preserve relevance gate and extend fixtures to trusted-source results. | Relevant and irrelevant retrieval controls. | Canonical trusted retrieval passes relevance gate. | Evaluator JSON/UI and test output. | Direct relevance evaluation exists with scope limitation. | NOT CLOSED
REQ-026 | PASS + LIMITATION | Evaluators receive response_text and retrieved documents; semantic battery covers summary claims and retrieved claims. | Search-result evaluation currently applies to synthetic FAISS results, not trusted external results. | Extend same evaluation contract to external RetrievedDocument results. | Evaluate one generated summary and one retrieved-result claim. | Canonical trusted-search workflow passes both evaluation layers. | Paired evaluation record and screenshot. | Both output types are evaluated in current limited source scope. | NOT CLOSED
REQ-027 | PARTIAL | assistant_pipeline.py logs one detailed run record; JSONL contains intent, state, response, evaluations, and memory. | No per-module event records or analysis by module. | Add structured module/tool events and an aggregation function. | Emit event per module and validate schema/outcome. | Canonical workflow produces complete ordered module trace. | Event log extract and metrics view. | Pipeline-level logging exists; per-module analysis does not. | NOT CLOSED
REQ-028 | PASS | booking_metrics.py aggregates persisted TOOL_EXECUTION events by book_appointment and outcome, excluding TOOL_SKIPPED; booking_metrics_view.py and Streamlit render the result. | No remaining gap after additive implementation; metric definition, denominator, malformed-record handling, and UI placement are explicit. | Preserve existing pipeline and logs; add a bounded persisted-event aggregation and independent UI panel. | Mixed persisted success/failure fixtures: 9 SUCCESS / 11 SUCCESS+FAILURE attempts = 81.82%; malformed rows skipped and counted; zero-attempt behavior returns N/A. | Operational Performance panel renders persisted metric without requiring a new workflow run. | Focused 10 passed; full regression 121 passed; persisted proof 9/11 = 81.82%; 52 records scanned; 0 malformed; memory unchanged; visible screenshot. | Booking-success metric is reproducible, persisted-event based, independently displayed, and excludes skipped steps from the denominator. | CLOSED
REQ-029 | PASS | response_precision_evaluator.py defines the claim-level contract; persisted_response_precision.py calculates the metric from pipeline_runs.jsonl; Streamlit renders the persisted result. | No remaining gap after component, persisted-log integration, and visible UI evidence. | Add a deterministic claim-level precision contract and connect it to persisted semantic-evaluation records without changing the semantic-faithfulness evaluator. | Known fixture: 3/4 = 75.00%; zero-claim behavior returns N/A; unsupported claims are excluded from the supported numerator. | Persisted multi-run log proof: 85/86 = 98.84%; 125-test full regression remains green. | Focused 14 passed; full regression 125 passed; visible Response Precision panel shows 98.84%, 85 supported, 86 verifiable, formula and basis. | Definition, deterministic calculation, persisted-log integration, and visible evidence all pass. | CLOSED
REQ-030 | PASS | app/ui/streamlit_app.py configures and renders the interactive dashboard. | Runtime UI launch was not repeated in this audit because project dependencies are unavailable locally; source and prior evidence exist. | Preserve; rerun in validated project environment during Phase 4. | Import/smoke test UI helpers where separable. | Launch Streamlit and run canonical scenario. | Full-dashboard screenshot and launch command/output. | Direct source implementation with verification limitation. | NOT CLOSED
REQ-031 | PASS | streamlit_app.py:42-101 accepts patient workflow request and displays assistant response; appointment, sources, and memory follow. | Patient ID is fixed to P001, appropriate only to the demo scope. | Preserve patient view; label role explicitly when adding doctor navigation. | Patient-view render/smoke checks. | Run canonical scenario through Patient View. | Patient View screenshot. | Distinct patient-facing workflow is present. | NOT CLOSED
REQ-032 | PASS | Distinct Patient View and Doctor View tabs consume existing serialized WorkflowState. Doctor View visibly presents doctor, specialty, assigned patient, patient ID, appointment time, reason, and status. | None for REQ-032. | Implemented without backend duplication. | PASS: Doctor View populated/unavailable contract tests (2/2); appointment-format positive/negative regression tests (2/2). | PASS: final canonical run produced deterministic PASS, semantic PASS, and accepted-for-memory YES; displayed authoritative appointment values. | Doctor View screenshot f8f2d903-176c-4b42-a51c-4ddb1c468b06.png; evaluation screenshot fd5c1d25-ba8a-444e-9d64-79cc4690fd01.png. | Literal doctor-facing view proven; appointment-time evaluator false negative corrected with bounded format recognition and negative control. | CLOSED
REQ-033 | PARTIAL | Streamlit displays the latest appointment time/status from last_run. | No appointment tracker/history or observable status updates beyond one static result. | Add session/state-backed appointment tracking sourced from booking results. | Create/update tracker records and validate status display. | Run booking and observe tracker update in same app session. | Before/after tracking screenshots. | Latest status is shown; real-time tracking behavior is incomplete. | NOT CLOSED
REQ-034 | PASS | streamlit_app.py:200-247 displays retrieved source title, type, URL when present, content, and distance for last_run. | Current sources are synthetic and lack URLs; trusted-source closure is separate. | Preserve display contract and feed trusted external results later. | Render retrieved-document variants with/without URL. | Canonical trusted retrieval appears in latest-run display. | Retrieved Sources screenshot. | Latest retrieved information is visibly summarized/displayed. | NOT CLOSED
REQ-035 | PASS | Evaluation Status explicitly labels Model Response Metrics and displays deterministic, semantic, and memory-acceptance outcomes. | None for model-response metric visibility. | Preserved existing evaluators and projected their results into a rubric-readable UI section. | PASS: model PASS/FAIL/ERROR and memory YES/NO projections tested. | PASS: full suite 10/10; canonical response displayed PASS/PASS/YES. | Three Evaluation Status screenshots captured 2026-09-03. | Model-response evaluation is explicitly labeled and directly visible. | CLOSED
REQ-036 | PASS | evaluation_metrics.py aggregates existing planning outcomes; Streamlit displays attempts, successes, failures, and success rate. | None for aggregate tool-success metrics. Event-level usage detail remains correctly reserved for Step 1.4. | Added presentation-only metric projection without changing graph/tools/logging. | PASS: 100%, 50%, and zero-attempt tool-metric cases tested. | PASS: full suite 10/10; canonical result displayed 5 attempted, 5 successful, 0 failed, 100%. | 5312cc2e-0773-4d7f-a877-72e49e3f0bc3.png; a7a26a90-22ce-4364-9fb8-d8f10b5f66ae.png; a6b1d66b-9a11-47c0-9051-dab4cafdaa08.png. | Aggregate tool-success indicators are visible; raw tool events remain Step 1.4 scope. | CLOSED
REQ-037 | PARTIAL | streamlit_app.py:251-284 displays stored memory fields/turn count; assistant_pipeline gates writes. | No memory read/write trace or provenance/timestamp/action display. | Emit safe memory events and display trace without exposing unnecessary patient data. | Memory write, recall, rejection, and clear events. | Canonical + follow-up scenario shows ordered memory trace. | Memory-trace screenshot and event log. | Memory state is visible; trace is not. | NOT CLOSED
REQ-038 | PASS | Planning View displays goal, basis, framework, five sub-goals, nodes, tools, status, and execution evidence. | None for explicit planning-breakdown visibility. | Implemented as a third Assistant Response tab using detailed-pipeline planning metadata. | PASS: three planner component tests; focused suite 7/7. | PASS: full suite 7/7 and canonical run PASS/PASS/YES. | a258b80f-00d4-4ece-8b70-294a4f3a5f14.png; adef6ba0-2073-43b7-92f1-501e109b1ed7.png; d2010770-9502-4ca7-b05f-642dab903b0c.png. | Literal planning breakdown is now visible and corresponds to actual WorkflowState outcomes. | CLOSED
REQ-039 | PARTIAL | Streamlit text area permits arbitrary request entry and Run Assistant execution. | Only one patient is selectable and the pipeline is strongly tuned to the canonical scenario; no curated multi-scenario controls/evidence. | Add small scenario selector/examples while preserving free-text input. | Execute supported canonical, follow-up, negative, and alternate-specialty scenarios. | Run multiple scenarios through Streamlit and record outcomes. | Scenario-selector and multi-run screenshots/results. | Interactive input exists; different-scenario coverage is incomplete. | NOT CLOSED
REQ-040 | OPEN | pipeline_logger.py writes whole-run JSONL records. | No per-tool invocation records, task association, or success/failure outcomes. | Instrument each deterministic tool boundary with structured events. | Verify event schema, success and exception cases for every tool. | Canonical and negative scenarios yield complete tool traces. | Tool log extract and UI success/failure view. | Run-level logging is not literal tool-usage logging. | NOT CLOSED

## Step 0.2 Summary
Phase 0 - Step 0.2 Compliance Assessment Summary
Status | Count | Control | Result | Evidence
PASS | 8 | Requirements mapped | PASS | 40/40 rows contain implementation, gap, component test, integration test, and evidence target.
PASS + LIMITATION | 4 | Application code modified | NO | Read-only extraction and inspection only.
PARTIAL | 15 | Core syntax | PASS | 30 application/data/test Python files parsed successfully by AST.
OPEN | 13 | Memory component test | PASS | tests/test_patient_memory.py completed all four checks.
|  | Full live regression | NOT RERUN | Local audit runtime lacks project dependencies (python-dotenv and others); existing JSONL evidence retained.
|  | Repository finding | OPEN | notebooks/main.py contains only a stray '+' and is invalid Python; outside canonical path but must be corrected before packaging.
Critical Path from the Controlling Plan
Doctor View -> medical-history add/update -> persistent patient context -> FAISS patient summaries -> trusted external retrieval -> metrics/logging/planning visibility -> full regression -> submission evidence
Step 0.2 Exit Decision
CLOSED as a mapping step. No functional requirement is CLOSED; implementation begins only after Step 0.3 freezes optional work and change control.
Phase 0 Exit Decision
Phase 0 remains CLOSED. Phase 1 Steps 1.1 Doctor View, 1.2 Planning/Goal-Decomposition, and 1.3 Model/Tool Evaluation Metrics are CLOSED with component, regression, canonical integration, dual-evaluation, memory-acceptance, and visible evidence. Next authorized work: Phase 1 Step 1.4 tool-event observability.

## Step 0.3 Change Control
Phase 0 - Step 0.3 ¦ Scope Freeze and Change-Control Baseline
Effective immediately: compliance-critical work only. Current Work configuration: GPT-5.6 Sol Light. Application code unchanged.
Control ID | Control | Required Behavior | Approval Authority | Verification | Status
CC-001 | Controlling specification | The official four-page Problem Statement controls scope and acceptance. Adjacent capability is not equivalence unless the source permits an equivalent. | Project Lead | Every change links to REQ-001 through REQ-040. | ACTIVE
CC-002 | No rebuild | Extend validated interfaces; do not replace the canonical architecture. | Project Lead | Architecture Delta records PRESERVED/ADDED/REMOVED/WHY. | ACTIVE
CC-003 | One controlled change | Modify one interface or architectural layer at a time; component-test it before integration. | Project Lead | One requirement/change package has its own component and integration evidence. | ACTIVE
CC-004 | Regression protection | Preserve structured interpretation -> LangGraph -> deterministic tools -> FAISS/RAG -> synthesis -> dual evaluation -> memory/logging -> Streamlit. | Project Lead | Canonical regression remains a mandatory gate after each integrated requirement package. | ACTIVE
CC-005 | Evidence-based closure | Syntax PASS is insufficient. No requirement closes without implementation, component test, integration test, and visible submission evidence. | Project Lead | Closure column changes only after all evidence fields are satisfied. | ACTIVE
CC-006 | Defect control | Any discovered regression or defect enters the findings register and remains OPEN until verified. | Project Lead | Finding has owner, remediation, test, and closure evidence. | ACTIVE
CC-007 | Optional-work freeze | No Docker, new agents, evaluator sophistication, portfolio features, refactoring, or unrelated enhancement during the compliance critical path. | Francisco Soto | Optional work remains deferred until every explicit requirement closes and final regression passes. | FROZEN
CC-008 | Model-change gate | Before changing the ChatGPT Work model/reasoning level, present current/proposed configuration, task rationale, Work-credit impact, duration, and reversion plan; Francisco must approve. | Francisco Soto | Approval is recorded before the model setting changes. | ACTIVE
CC-009 | API-model gate | Do not change an application LLM, embedding, or evaluator model identifier without presenting purpose, expected calls, token/cost effect, regression risk, and reversion plan. | Francisco Soto | Explicit approval precedes code edit or first live use of the new model. | ACTIVE
CC-010 | Live-API cost gate | Prefer deterministic/mock verification during development. Run live API-dependent tests only when required for component or gate-level evidence. | Project Lead | Test record distinguishes no-cost local tests from live API calls. | ACTIVE
CC-011 | Runtime evidence rule | Current terminal/runtime evidence overrides earlier assumptions; retain prior evidence only when the current run cannot be performed and label the limitation. | Project Lead | Register identifies evidence date/source and any rerun limitation. | ACTIVE
CC-012 | Packaging integrity | Keep credentials, .env files, virtual environments, caches, and noncanonical invalid artifacts out of the submission package. | Project Lead | Final package audit passes; notebooks/main.py finding resolved before packaging. | ACTIVE
Authorized Critical-Path Sequence
Order | Work Package | Plan Reference | State | Requirement Link | Gate
1 | Doctor View | Phase 1.1 | Not started | REQ-032 | Next authorized implementation
2 | Medical-history add/update | Phase 2.1-2.4 | Not started | REQ-002/003/009 | After UI observability package
3 | Persistent patient context | Phase 2.5 | Not started | REQ-013/018 | After record mutation
4 | FAISS patient summaries | Phase 2.6 | Completed | REQ-011/012 | CLOSED - 4/4 focused, live integration PASS, 59/59 regression
5 | Trusted external retrieval | Phase 3 | Not started | REQ-004/010/022/026 | After data/memory closure
6 | Metrics/logging/planning visibility | Phase 1.2-1.4 + reconciliation | Not started | REQ-005-007/014-018/027-029/036-040 | Controlled requirement packages
7 | Full compliance regression | Phase 4 | Not started | All requirements | No unresolved regression
8 | Submission evidence | Phase 5 | Not started | All requirements | After code freeze
9 | Optional Docker | Post-critical path | DEFERRED | Optional | Only after explicit requirements close and final regression passes
Model / API Approval Request Template
Current configuration | GPT-5.6 Sol Light for ChatGPT Work; application API model identifiers unchanged
Proposed configuration | Enter before requesting approval
Scope | Work model / application LLM / embedding / evaluator
Technical reason | Enter requirement-specific rationale
Cost effect | State Work-credit and/or API-token effect separately
Expected live calls | Enter estimate or 'none'
Duration | Enter bounded task or gate
Regression risk | Enter affected interfaces/tests
Reversion plan | Enter exact rollback point; DO NOT CHANGE UNTIL FRANCISCO APPROVES

## Step 1.1 Doctor View
Phase 1 - Step 1.1 Doctor View Compliance Record
Acceptance Element | Finding | Status | Evidence | Architecture Alignment | AI Enablement Lead Lens | FDE Lens | Next Gate
Source Requirement | Build a Streamlit dashboard that enables patient and doctor views. | CONTROL | Official Problem Statement, page 4 | Presentation-layer requirement | Role-aligned adoption surface | Translate stakeholder requirement literally | N/A
Literal Interpretation | Provide a distinct, identifiable doctor-facing view. | CONTROL | Adjacent appointment summary is not treated as equivalent | No backend duplication | Supports clinician review | Use minimum compliant interface | N/A
Plan Acceptance | Show doctor, specialty, assigned patient, appointment time, reason, and status. | CONTROL | 100% Compliance Project Plan, Step 1.1 | Fields already exist in WorkflowState | Makes workflow output usable | Maps data contract to user need | N/A
Existing Implementation | Patient workflow UI and appointment summary existed; no distinct Doctor View. | GAP CONFIRMED | Step 0.2 mapping for REQ-032 | Canonical workflow preserved | Existing capability was not overstated | Requirement-to-interface trace | N/A
Smallest Compliant Implementation | Add pure Doctor View projection and labeled Patient View/Doctor View tabs. | IMPLEMENTED | app/ui/doctor_view.py; app/ui/streamlit_app.py | Consumes serialized workflow output only | Clear clinician review surface | Bounded presentation-layer adaptation | N/A
Component Test | Validate all required fields and safe unavailable-state behavior. | PASS | tests/test_doctor_view.py: 2/2 assertions passed | Tests projection independently | Predictable degraded state | Test at interface contract | N/A
Source Regression | Parse all application and test Python source. | PASS | AST regression: 30 files | No syntax regression detected | Preserves validated foundation | Controls change risk | N/A
Integration Test | Run canonical booking and compare Doctor View with authoritative WorkflowState. | PASS | Final canonical run: deterministic PASS, semantic PASS, accepted for memory YES; evaluation screenshot captured. | Must traverse existing pipeline | Confirms end-user workflow | Validate deployed boundary | CLOSED
Visible Evidence | Capture the rendered Doctor View after canonical booking. | PASS | Doctor View screenshot captured with doctor, specialty, assigned patient, patient ID, appointment time, reason, and status. | Evidence must come from actual UI | Evaluator-readable proof | Operational verification | CLOSED
Step 1.1 Decision: CLOSED - REQ-032 passed the complete requirement-to-evidence chain

## Step 1.2 Planning
Phase 1 - Step 1.2 Planning and Goal-Decomposition Closure Record
Acceptance | Finding | Status | Evidence | Implementation | Architecture Alignment | AI Enablement Lead Lens | FDE Lens
Source Requirement | Planner interpretation; sequential sub-goals; tools/APIs; displayed planning breakdown. | CONFIRMED | Official Problem Statement Part 1 §1 and Part 2 §8. | Controlling source used literally. | Applies to planning/observability layers. | Makes agent decisions inspectable. | Creates reviewer-to-runtime traceability.
Literal Interpretation | A multi-step request must yield an explicit ordered plan naming actual execution mechanisms. | CONFIRMED | REQ-005, REQ-006, REQ-007, REQ-038. | No adjacent capability counted as compliance. | Separates intent, plan, and execution. | Defines a testable delivery contract. | Prevents architecture-only claims.
Existing Implementation | RequestIntent and fixed LangGraph sequence already existed. | PRESERVED | request_interpreter.py; healthcare_graph.py. | Reused validated structures. | No graph redesign. | Avoided added model cost. | Reduced field-change risk.
Gap | Plan, sub-goals, tool selection, and outcomes were not explicitly displayed. | CLOSED | Phase 0.2 mapping for four requirements. | Added only missing observability contract. | Preserved deterministic authority. | Closed a governance visibility gap. | Turned implicit behavior into evidence.
Smallest Implementation | Planner projection plus detailed-result integration and Planning View tab. | ADDED | workflow_planner.py; assistant_pipeline.py; streamlit_app.py. | No model or prompt change. | RequestIntent -> plan -> unchanged LangGraph. | Cost-neutral planning metadata. | Exact node/tool/capability mapping.
Component Test | Plan order, tool mapping, success outcomes, and incomplete step tested. | PASS | tests/test_workflow_planner.py; focused suite 7/7. | Pure deterministic tests. | Existing Doctor View/evaluator tests retained. | No API charge. | Positive and negative operational signals.
Integration Test | Full local automated suite passed after transfer. | PASS | python -m pytest -q: 7 passed in 3.30s. | No regression detected. | Planning coexists with existing pipeline. | Staged validation before live use. | Deployment preflight passed.
Canonical Live Test | Existing canonical request completed once. | PASS | Deterministic PASS; Semantic PASS; Accepted for Memory YES. | One approved live run only. | Full workflow remained valid. | Cost gate honored; no model change. | End-to-end production-like evidence.
Visible Evidence | All five steps showed nodes, tools, capabilities, COMPLETED, and state evidence. | PASS | Three Planning View screenshots captured 2026-09-03. | Distinct third Assistant Response tab. | Evidence sourced from detailed result. | Inspectable execution reasoning. | Reviewer can trace goal to result.
Delta | Preserved architecture; added planning visibility/tests; removed nothing. | CONFIRMED | Delta Log rows 29-32. | Bounded additive closure. | Canonical contract retained. | No new token-consuming stage. | Rollback backups created locally.
Evidence files: a258b80f-00d4-4ece-8b70-294a4f3a5f14.png ¦ adef6ba0-2073-43b7-92f1-501e109b1ed7.png ¦ d2010770-9502-4ca7-b05f-642dab903b0c.png
Step 1.2 Decision: CLOSED - REQ-005, REQ-006, REQ-007, and REQ-038 passed the complete requirement-to-evidence chain

## Step 1.3 Metrics
Phase 1 - Step 1.3 Model and Tool Evaluation Metrics Closure Record
Acceptance | Finding | Status | Evidence | Implementation | Architecture Alignment | AI Enablement Lead Lens | FDE Lens
Source Requirement | Dashboard evaluation metrics for model responses and tool success. | CONFIRMED | Official Problem Statement Part 2 §7. | Controlling source used literally. | Presentation and observability scope. | Makes quality gates visible. | Makes operational health scannable.
Literal Interpretation | Reviewer sees labeled model outcomes and calculated tool indicators. | CONFIRMED | REQ-035 and REQ-036. | No inference from adjacent diagnostics accepted. | Separates metrics from raw events. | Supports rubric readability. | Defines an observable run contract.
Existing Implementation | Deterministic, semantic, and memory outcomes were visible; tool outcomes existed only per planning step. | PRESERVED | streamlit_app.py; planning payload. | Reused validated results. | No evaluator redesign. | Avoided added model cost. | Retained detailed planning evidence.
Gap | Tool attempts/successes/failures/rate were not aggregated as dashboard metrics. | CLOSED | Phase 0.2 REQ-036 mapping. | Added only missing metric projection. | No workflow mutation. | Closed a visibility gap. | Improved deployment-status readability.
Smallest Implementation | Pure evaluation_metrics projection and rubric-readable Streamlit sections. | ADDED | evaluation_metrics.py; streamlit_app.py. | No pipeline change. | Existing result -> metrics -> UI. | No additional inference call. | Aggregate metrics; events deferred to Step 1.4.
Component Test | Healthy, partial-failure, and zero-attempt cases verified. | PASS | test_evaluation_metrics.py: 3 tests; focused suite 10/10. | Deterministic projection tests. | Prior Phase 1 tests retained. | No API charge. | Covers operational edge cases.
Integration Test | Complete collected suite passed after transfer. | PASS | python -m pytest -q: 10 passed in 2.52s. | No regression detected. | Metrics coexist with all three views. | Staged validation before live use. | Deployment preflight passed.
Canonical Live Test | Canonical request completed successfully in the updated interface. | PASS | Deterministic PASS; Semantic PASS; Memory YES. | Single evidence run; no rerun needed. | Full workflow remained valid. | No model change. | Production-like metric population.
Visible Evidence | Model PASS/PASS/YES and tool 5/5/0/100% displayed. | PASS | Three screenshots captured 2026-09-03. | Rubric-readable Evaluation Status. | Derived from actual run result. | Transparent model/tool health. | Immediate success/failure assessment.
Delta | Preserved architecture; added metrics/tests; removed nothing. | CONFIRMED | Delta Log rows 34-37. | Bounded presentation change. | Step 1.4 event boundary retained. | Cost-neutral computation. | Rollback backup verified locally.
Evidence files: 5312cc2e-0773-4d7f-a877-72e49e3f0bc3.png ¦ a7a26a90-22ce-4364-9fb8-d8f10b5f66ae.png ¦ a6b1d66b-9a11-47c0-9051-dab4cafdaa08.png
Step 1.3 Decision: CLOSED - REQ-035 and REQ-036 passed the complete requirement-to-evidence chain

## Step 1.4 Tool Events
Phase 1 - Step 1.4 Tool Usage and Success/Failure Event Closure Record
Acceptance | Finding | Status | Evidence | Implementation | Architecture Alignment | AI Enablement Lead Lens | FDE Lens
Source Requirement | Log tool usage and success/failure across tasks. | CONFIRMED | Official Problem Statement Part 2 §8; REQ-040. | Controlling source used literally. | Observability scope. | Makes execution auditable. | Exposes operational run events.
Literal Interpretation | Reviewer can identify each tool, task/node association, and success/failure outcome. | CONFIRMED | REQ-040 minimum acceptance. | No aggregate-only substitute accepted. | Separates metrics from events. | Supports transparent enablement. | Defines an inspectable run contract.
Existing Implementation | Whole-run JSONL logging and aggregate tool metrics existed, but no explicit per-tool event records. | PRESERVED | pipeline_logger.py; evaluation_metrics.py. | Reused the validated logger. | No graph redesign. | No added model cost. | Retained prior diagnostic evidence.
Gap | Logs did not identify individual tool outcomes or task associations. | CLOSED | Phase 0.2 REQ-040 mapping. | Added only the missing event contract. | No workflow mutation. | Closed an auditability gap. | Improved incident inspection.
Smallest Implementation | Project planning outcomes into ordered TOOL_EXECUTION records; include them in run_result and display them in Workflow Diagnostics. | ADDED | tool_events.py; assistant_pipeline.py; streamlit_app.py. | Existing run_result -> logger and UI. | No model, prompt, or tool change. | Cost-neutral projection. | Deployable observability increment.
Component Test | Success, failure, ordering, fields, and temporary JSONL persistence verified. | PASS | test_tool_events.py: 3 tests. | Deterministic tests only. | Prior capabilities retained. | No API charge. | Covers logging contract.
Integration Test | Complete local regression suite passed after implementation. | PASS | python -m pytest -q: 13 passed in 4.00s. | No regression detected. | All three views remain valid. | Staged validation before live use. | Deployment preflight passed.
Canonical Live Test | Canonical healthcare request completed after one transient connection retry. | PASS | Deterministic PASS; Semantic PASS; Memory YES; tools 5/5/0/100%. | No model change. | Full workflow remained valid. | Retry was explicitly approved. | Transient network failure distinguished from application behavior.
Visible and Persisted Evidence | Workflow Diagnostics displayed five ordered SUCCESS events, and pipeline_runs.jsonl contained the same five records. | PASS | UI screenshots plus read-only JSONL terminal inspection. | One event contract serves UI and log. | Reviewer can inspect tool, node, status, evidence. | Traceable execution without added inference. | Operational diagnosis is direct.
Delta | Preserved architecture; added event projection, persistence test, and diagnostics table; removed nothing. | CONFIRMED | Delta Log rows 39-42. | Bounded observability change. | Phase 1 closure boundary maintained. | Cost-neutral except approved canonical validation. | Rollback backups verified locally.
Evidence files: 7964edc6-c815-415b-a691-d5be210d5bc6.png ¦ 1e748ca1-0a96-4be1-946a-2ec312003b40.png ¦ 8e5b3b1d-7a5a-40ad-9b40-9f8e9b9c0807.png ¦ 3c3ab1d6-5cc3-4de0-ab30-3d0cd27929ba.png
Step 1.4 Decision: CLOSED - REQ-040 passed the complete requirement-to-evidence chain

## Step 1.5 UI Regression
PHASE 1 · STEP 1.5 — STREAMLIT UI REGRESSION
Acceptance Stage | Finding | Status | Evidence | Implementation | Architecture Alignment | AI Enablement Lead Lens | Forward-Deployed Engineer Lens
Source Requirement | Run Streamlit UI regression for patient and doctor views. | VERIFIED | Controlling plan, Phase 1 Step 1.5 | Regression gate only | No redesign authorized | Confirms user-facing evaluation evidence remains legible | Validates the deployed workflow surface after telemetry changes
Literal Interpretation | Both views must operate without breaking the canonical scenario. | VERIFIED | Fresh canonical run | Inspect both tabs from the same run | Uses existing view boundaries | Checks human-readable response and metrics | Checks role-specific operational rendering
Existing Implementation | Distinct Patient View and Doctor View remained available. | PRESERVED | Patient and doctor screenshots | Existing Streamlit tabs | Preserves established UI structure | Retains evaluation and memory visibility | Retains clinician-facing assignment view
Gap | Post-Step 1.4 regression evidence was required. | CLOSED | Fresh evidence captured | No functional gap found | No architecture change required | Evaluation status remained PASS/PASS/YES | Tool-event diagnostics remained visible
Smallest Compliant Implementation | No code change; execute and document regression only. | COMPLETE | Step 1.5 evidence set | Verification only | Avoided unnecessary mutation | Protected evaluated behavior | Minimized deployment risk
Canonical Live Test | One explicitly approved canonical regression completed. | PASS | Fresh Streamlit run | Patient P001 / Robert Smith / CKD / Nephrology | Existing pipeline exercised end-to-end | Deterministic PASS; Semantic PASS; Accepted YES | Five ordered tool events completed successfully
Patient View | Patient, medical record, selected doctor, appointment, educational context, evaluation, memory, and diagnostics rendered. | PASS | edf87574-7218-4717-a9f8-3e6cd9ab6560.png | Existing Patient View | Canonical data flow preserved | Rubric-readable evidence remained visible | Operational state and sources remained inspectable
Doctor View | Doctor, specialty, assigned patient, appointment time, reason, status, evaluation, memory, and diagnostics rendered. | PASS | a1f0b354-32c1-4fda-8fd7-383395ff0644.png | Existing Doctor View | Role-specific projection preserved | Evaluation outcome remained consistent across views | Assignment data remained deployment-readable
Automated Regression | Full local suite completed after the UI regression. | PASS | 13 passed in 1.45s | python -m pytest -q | All prior tests preserved | Evaluation and event contracts remained covered | No regression detected across integrated components
Delta | PRESERVED existing behavior; ADDED closure evidence; REMOVED nothing. | RECORDED | Delta Log rows 44–47 | No application-code delta | Smallest compliant closure | Evidence-backed acceptance | Low-risk transition to Phase 2 inspection
Evidence Files | Three fresh artifacts retained with the Phase 1 checkpoint. | RETAINED | Patient View; Doctor View; 13-test terminal result | Sanitized evidence package | No secrets or runtime environment included | Traceable UI and evaluation proof | Portable handoff evidence
Decision | Step 1.5 CLOSED; Phase 1 CLOSED. Phase 2 Step 2.1 is the next authorized activity. | CLOSED | Both views passed; 13/13 tests passed | Proceed only with Step 2.1 inspection | Phase boundary explicitly controlled | Acceptance chain complete | Ready for interface audit before modification

## Step 2.2 Record Mutations
PHASE 2 · STEP 2.2 — STRUCTURED HISTORY MUTATIONS
Acceptance Stage | Finding | Status | Evidence | Implementation | Architecture Alignment | AI Enablement Lead Lens | Forward-Deployed Engineer Lens
Source Requirement | Enable attendants to add or update structured/unstructured patient history. | PARTIAL | Problem statement: Manage medical records | Step 2.2 addresses structured history only | REQ-002 remains open | Separates deterministic data mutation from generative behavior | Constrains change to an inspectable operational boundary
Literal Interpretation | Structured diagnoses, medications, and treatment notes require deterministic add/update behavior. | VERIFIED | Step 2.1 mutation-boundary inspection | Operate on supplied MedicalRecord collection | Preserves existing retrieval contract | Reduces hallucination and uncontrolled state change | Supports predictable field-level operations
Existing Implementation | MedicalRecord already contained three structured lists; tool supported retrieval only. | PRESERVED | medical_record.py and medical_record_tools.py | Extended existing tool module | No schema change required | Reuses authoritative structured data | Avoids unnecessary storage redesign
Gap | No deterministic mutation interface or component tests existed. | CLOSED | New add/update functions and test suite | Explicit result statuses | Graph and UI unchanged | Failures remain machine-readable | Operational errors are distinguishable
Smallest Compliant Implementation | Add/update only the three existing structured fields. | COMPLETE | medical_record_tools.py | No persistence or UI in this step | One interface changed | Bounded, auditable capability | Low-risk incremental deployment
Add Behavior | Validated values append to the authoritative record object. | PASS | Parameterized diagnosis, medication, and treatment-note tests | Whitespace normalized; case-insensitive duplicate protection | Existing record identity retained | Deterministic state transition | Authoritative state immediately reflects success
Update Behavior | Exact current entry is replaced in its existing list position. | PASS | Update and missing-entry tests | Duplicate replacement rejected | List order preserved | Predictable update semantics | No silent overwrite or append
Failure Contract | Invalid field/value, duplicate, unknown patient, and missing entry return explicit statuses. | PASS | Negative-path component tests | No uncontrolled AttributeError | Safe tool boundary | Evaluation-ready error semantics | Troubleshooting evidence is actionable
Component Test | Isolated structured-history suite passed. | PASS | 13 passed in 0.08s | tests/test_medical_record_mutations.py | No API call | Covers success and boundary conditions | Fast deterministic verification
Integration Regression | Complete local pytest suite passed. | PASS | 26 passed in 2.30s | python -m pytest -q | All Phase 1 behavior preserved | Existing evaluation contracts retained | No detected cross-component regression
Delta | PRESERVED canonical architecture; ADDED structured mutation interface/tests; REMOVED nothing. | RECORDED | Delta Log rows 49–52 | Two authorized files changed | No unrelated feature expansion | Acceptance evidence retained | Ready for unstructured-note interface
Decision | Step 2.2 CLOSED. REQ-002 remains OPEN. Step 2.3 is next. | CLOSED | 13/13 component and 26/26 regression tests | Proceed to unstructured history only | Phase boundary controlled | Structured capability verified | No live canonical/API test required for this deterministic component

## Step 2.3 History Notes
PHASE 2 · STEP 2.3 — UNSTRUCTURED HISTORY NOTES
Acceptance Stage | Finding | Status | Evidence | Implementation | Architecture Alignment | AI Enablement Lead Lens | Forward-Deployed Engineer Lens
Source Requirement | Enable attendants to add or update structured/unstructured patient history. | PARTIAL | Problem statement: Manage medical records | Step 2.3 closes the unstructured data path | REQ-002 remains open pending UI | Separates deterministic mutation from generation | Maintains an inspectable operational boundary
Literal Interpretation | MedicalRecord requires a free-text note collection with deterministic add/update operations. | VERIFIED | Step 2.1 inspection and Step 2.2 boundary | Add history_notes with default empty list | Backward-compatible schema extension | Preserves source-authored text | Supports predictable field-level operations
Existing Implementation | Three structured lists and their mutation interface existed. | PRESERVED | Step 2.2 CLOSED checkpoint | Extend rather than replace | Structured contract unchanged | Retains validated state behavior | Avoids unnecessary redesign
Gap | No distinct unstructured history-note field or tools existed. | CLOSED | Schema, tools, and tests added | Explicit result statuses | Graph and UI unchanged | Failures remain machine-readable | Operational errors are actionable
Smallest Compliant Implementation | One history_notes list plus add/update functions. | COMPLETE | medical_record.py and medical_record_tools.py | No persistence or UI in this step | Two interfaces extended | Bounded auditable capability | Low-risk incremental deployment
Free-Text Preservation | Leading/trailing whitespace is trimmed; internal line breaks are preserved. | PASS | Multiline component test | Unstructured content remains unstructured | No forced schema decomposition | Protects human-authored context | Maintains usable clinical narrative
Mutation Behavior | Validated notes append or replace in the authoritative record object. | PASS | Add/update and position tests | Duplicate replacement rejected | Record identity and order preserved | Deterministic state transitions | No silent overwrite
Failure Contract | Empty, duplicate, missing-entry, and unknown-patient cases return explicit statuses. | PASS | Negative-path tests | No uncontrolled exceptions | Safe tool boundary | Evaluation-ready semantics | Troubleshooting evidence is actionable
Component Test | Isolated unstructured-history suite passed. | PASS | 12 passed in 0.06s | tests/test_unstructured_history_notes.py | No API call | Success and boundary behavior covered | Fast deterministic verification
Integration Regression | Complete local pytest suite passed. | PASS | 38 passed in 2.25s | python -m pytest -q | All prior behavior preserved | Existing evaluation contracts retained | No detected cross-component regression
Delta | PRESERVED prior behavior; ADDED note schema/tools/tests; REMOVED nothing. | RECORDED | Delta Log rows 54–57 | Three authorized files changed | No unrelated expansion | Evidence-backed acceptance | Ready for attendant UI
Decision | Step 2.3 CLOSED. REQ-002 remains OPEN. Step 2.4 is next. | CLOSED | 12/12 component and 38/38 regression tests | Proceed to attendant UI only | Phase boundary controlled | Unstructured data path verified | No live canonical/API test required

## Step 2.4 Attendant UI
PHASE 2 · STEP 2.4 — ATTENDANT HISTORY MANAGEMENT
Acceptance Stage | Finding | Status | Evidence | Implementation | Architecture Alignment | AI Enablement Lead Lens | Forward-Deployed Engineer Lens
Source Requirement | Enable attendants to add or update structured/unstructured patient history. | PASS | Problem statement: Manage medical records | Steps 2.2–2.4 complete the requirement chain | REQ-002 closed only after visible UI evidence | Authorized user capability is explicit | Human-facing operational boundary is inspectable
Literal Interpretation | An attendant-facing interaction must invoke all four mutation paths and expose resulting record state. | VERIFIED | Step 2.1 inspection and Steps 2.2–2.3 contracts | Add/update for structured and unstructured history | Presentation delegates to deterministic tools | Separates human interaction from business logic | Predictable dispatch and state transitions
Existing Implementation | Deterministic mutation tools existed without an attendant interaction. | PRESERVED | Steps 2.2 and 2.3 CLOSED checkpoints | Extend rather than replace | Graph, prompts, models, evaluation, and memory unchanged | Retains validated service contracts | Minimizes deployment risk
Gap | No Streamlit control supported authorized history management. | CLOSED | UI screenshots and dispatcher tests | Role-labeled attendant expander added | No workflow redesign | Closes a user enablement gap | Provides observable operator control
Smallest Compliant Implementation | Streamlit controls plus one pure dispatcher over existing tools. | COMPLETE | history_management.py and streamlit_app.py | Type, action, field, current, and replacement inputs | Thin UI boundary over deterministic mutations | Reusable enablement pattern | Low-risk incremental integration
Structured Add / Update | PASS — add, update, retrieval, duplicate, and empty-value paths visibly exercised. | PASS | Structured UI screenshots | Diagnoses state mutated and restored correctly | No silent overwrite | Clear success and failure feedback | Actionable operator evidence
Unstructured Add / Update | PASS — note added, replaced, and displayed in Current Medical History. | PASS | Unstructured UI screenshots | History Notes reflects latest text | Free text remains unstructured | Preserves human-authored clinical context | Visible authoritative state
Safeguards | Duplicate and empty replacements returned explicit non-mutating errors. | PASS | Negative-path UI evidence | Existing deterministic status contract reused | No uncontrolled exception | Errors are understandable | Troubleshooting signal is actionable
Component Test | History-management dispatcher suite passed. | PASS | 8 passed in 0.06s | tests/test_history_management.py | No API call | Boundary behavior covered | Fast deterministic verification
Integration / Runtime | Full suite passed after correcting an exposed last_run UI guard. | PASS | 46 passed in 1.05s | patient_view guard restored; no business logic changed | Canonical workflow retained | Regression evidence is transparent | Runtime defect discovered and closed
Delta | PRESERVED architecture; ADDED dispatcher/UI/tests; CORRECTED guard; REMOVED nothing. | RECORDED | Delta Log rows 59–62 | Three authorized files plus bounded correction | No unrelated expansion | Evidence-backed acceptance | Ready for persistence step
Decision | Step 2.4 CLOSED. REQ-002 PASS. Step 2.5 is next. | CLOSED | 8/8 component, 46/46 regression, and four visible UI behaviors | Persistence remains Step 2.5 / REQ-009 | Phase boundary controlled | Attendant capability verified | No live model/API call required

## Step 2.5 Persistence
PHASE 2 · STEP 2.5 — DURABLE PATIENT-HISTORY PERSISTENCE
Acceptance Stage | Finding | Status | Evidence | Implementation | Architecture Alignment | AI Enablement Lead Lens | Forward-Deployed Engineer Lens
Source Requirement | Integrate medical-history management through an EHR database or Patient database. | PASS | REQ-009 acceptance target | Versioned local Patient DB abstraction | PoC persistence boundary is explicit | Operational capability survives restart | Storage interface is replaceable
Literal Interpretation | Accepted MedicalRecord changes must persist and be retrievable after application restart. | VERIFIED | Disk and second-process UI evidence | Save, stop, restart, load, display | End-to-end state lifecycle verified | User-visible continuity established | Restart behavior is inspectable
Existing Implementation | Step 2.4 mutations changed only in-memory objects. | PRESERVED | Step 2.4 CLOSED checkpoint | Wrap rather than rewrite mutation logic | Graph and domain models unchanged | Retains validated interaction | Limits integration risk
Gap | All history changes were lost when Python restarted. | CLOSED | Exact note recovered after restart | Startup loads durable store | No hidden session dependency | Closes operational continuity gap | Failure mode directly tested
Smallest Compliant Implementation | Versioned JSON store plus transactional persistence wrapper. | COMPLETE | medical_record_store.py and history_management.py | Atomic os.replace; schema validation; rollback | Bounded Patient DB abstraction | Clear upgrade path to external EHR | Interface isolates storage technology
Structured / Unstructured | Both history forms serialize and reload through the MedicalRecord schema. | PASS | Focused restart tests | Pydantic dump and validation | One contract for both data forms | Consistent operator behavior | Schema-controlled round trip
Failure Safety | Rejected mutations do not rewrite storage; failed writes restore memory. | PASS | Negative-path tests | Explicit PERSISTENCE_ERROR | No silent partial commit | Actionable user feedback | Transactional behavior at PoC scale
Data Governance | Runtime record file is excluded from source control. | PASS | .gitignore evidence | data/medical_records.json ignored | Patient state separated from code | Reduces accidental disclosure risk | Deployment artifact remains clean
Component Test | Focused persistence suite passed. | PASS | 9 passed in 0.17s | tests/test_medical_record_persistence.py | No API call | Storage contract covered | Fast deterministic verification
Integration / Restart | Full suite and visible restart retrieval passed. | PASS | 55 passed; exact note visible after restart | New Streamlit process loaded saved record | Canonical workflow retained | Evidence proves user continuity | Runtime integration independently observable
Delta | PRESERVED architecture; ADDED store/wrapper/tests; REMOVED nothing. | RECORDED | Delta Log rows 64–67 | Six Python files plus .gitignore rule | No unrelated expansion | Evidence-backed acceptance | Ready for next controlled step
Decision | Step 2.5 CLOSED. REQ-009 PASS. | CLOSED | 9/9 component, 55/55 regression, disk and visible restart evidence | Local JSON is the bounded PoC Patient DB | Phase boundary controlled | Durable history verified | No live model/API call required

## Step 2.6 FAISS Summaries
PHASE 2 · STEP 2.6 — FAISS PATIENT-SUMMARY STORAGE AND RETRIEVAL
Acceptance Stage | Finding | Status | Evidence | Implementation | Architecture Alignment | AI Enablement Lead Lens | Forward-Deployed Engineer Lens
Source Requirement | Use a vector database such as FAISS to store and retrieve patient summaries. | PASS | REQ-011 / REQ-012 | Patient-summary vector index | Extends existing FAISS layer | Required capability is demonstrable | Existing architecture is preserved
Literal Interpretation | Embed a patient summary with identity metadata and retrieve it for the correct patient. | VERIFIED | P001 and R001 in live trace | PatientSummary contract | Identity stays explicit | Outcome is operator-verifiable | Trace supports diagnosis
Existing Implementation | FAISS indexed only synthetic educational documents. | PRESERVED | Prior RAG path remains | Separate patient-summary module | No knowledge-index rewrite | Reduces change exposure | Limits regression surface
Gap | No patient-summary object, metadata, scoped retrieval, or workflow path. | CLOSED | Focused and live evidence | New model, builder, search, graph node | Smallest compliant extension | Requirement maps to visible behavior | Gap closure is testable
Storage | Summary vectors are added to FAISS IndexFlatL2 with patient_id and record_id metadata. | PASS | 4/4 focused tests | Unchanged embedding interface | Uses established dependency | Model choice stays controlled | Implementation is replaceable
Retrieval Isolation | Candidates are filtered by patient_id before vector search. | PASS | Cross-patient isolation test | Identity-scoped candidate set | No post-search leakage window | Privacy boundary is explicit | Failure mode is directly tested
Durable-State Alignment | Summaries rebuild from the current durable MedicalRecord state. | PASS | Step 2.5 note appeared live | No stale index cache | Persistence remains source of truth | Operator edits flow downstream | State lifecycle stays coherent
Workflow Integration | LangGraph retrieves the patient summary after the medical record. | PASS | One P001/R001 result; zero errors | retrieve_patient_summary node | Canonical sequence extended | Execution is observable | Integration point is bounded
Component Test | Local deterministic embedding tests passed without API calls. | PASS | 4 passed in 2.84s | Dependency injection | Fast repeatable gate | Cost-aware verification | Offline failure isolation
Live / Regression | Approved live workflow and final suite passed. | PASS | REQ-011 PASS; REQ-012 PASS; 59 passed | Existing model identifiers unchanged | End-to-end behavior verified | Evidence meets evaluator needs | Regression risk controlled
Delta | PRESERVED architecture; ADDED scoped summary index; REMOVED nothing. | RECORDED | Delta Log rows 69–72 | Five-file change package | No optional scope expansion | Change is explainable | Rollback backup retained
Decision | Step 2.6 CLOSED. REQ-011 and REQ-012 PASS. | CLOSED | Focused, live, isolation, durable-state, and regression evidence | FAISS patient-summary path operational | Phase 2 requirement closure advanced | Capability and boundary are clear | Ready for Phase 3 source-contract gate